## Sheet1
Feature	Work	Relevance	Done?					Work:
Remaining functions in basicoperations.cc	1	1	x	1				1	Can practically copy it
Bergman fan from flats	2	1	x	2				2	Small adjustments, some renaming
cdd_helper_functions	2	3	x	2				3	Significant change
coarsen	2	1	x	2
complexify	2	1	x	2				Relevance:
create_curves.cc	1	1	x	1				1	Bonus content
diagonal_functions	0	0		0	WE DONT DO THIS, INSTEAD			2	Should be done for presentation, can do without
fan_diagonal	1	1	x	1	DO MATROID_FLAT FUNCTIONS!			3	Essential features, should work on presentation
piecewise_divisor	1	2	x	1
function_visual	1	1	x	1
hurwitz_cycles (need evaluation stuff) (DEPRECATED?)	2	1	x	2
hurwitz_combinatorial	2	2	x	2
intersection (rec fan and degree)	2	3	x	2
irreducible	1	2	x	1
is_smooth	3	1		0
check_cycle_equality	1	1	x	1
lines_in_cubic stuff	2	2	x	2
localize	1	2	x	1
matrod_from_fan	2	1	x	2
minkowsi_intersection	1	3	x	1
moduli_local (needs pruefer)	1	2	x	1
Introduce morphisms	3	3	x	3
morphism arithmetic and composition	3	3	x	3
pullbacks	3	3	x	3
morphism_special	2	3	x	2
pruefer.cc	1	2	x	1
psi classes	1	3	x	1
cutting_functions	1	1	x	1
tropical cube	2	1	x	2
insert_rays / triangulate	2	1	x	2
	49	Done:	94%	46